ORANGEHRM

# MASTER TEST PLAN

Functional validation of OrangeHRM Open Source demo

| Document ID | OHRM-TP-001 |
| --- | --- |
| Version | 1.0 |
| Status | Draft for Review |
| Prepared Date | 2 September 2026 |
| Planned Test Window | 7 September 2026 to 2 October 2026 |
| Application URL | https://opensource-demo.orangehrmlive.com/web/index.php/auth/login |

Planning basis This plan consolidates the user stories, RTM, test cases, and test data prepared for OrangeHRM. Dates, staffing, and environment details are proposed planning assumptions and can be updated after stakeholder review.

# 1. Document Control and Purpose

This document defines the scope, objectives, strategy, environment, test data, resources, deliverables, schedule, entry and exit criteria, risks, governance, and approval process for testing the OrangeHRM demo application.

| Role | Name | Responsibility | Approval |
| --- | --- | --- | --- |
| Test Plan Author | To be assigned | Prepare and maintain the plan | Pending |
| QA Lead / Reviewer | To be assigned | Review scope, estimates, coverage, and risks | Pending |
| Business / Product Stakeholder | To be assigned | Confirm business priorities and acceptance | Pending |
| Technical / Environment Owner | To be assigned | Confirm build, access, integrations, and environment | Pending |

## 1.1 References and Existing Deliverables

| Artifact | Purpose |
| --- | --- |
| OrangeHRM User Stories | Defines Login, Forgot Password, and Social Media Links requirements and acceptance criteria. |
| Requirement Traceability Matrix | Maps requirement IDs to finalized test cases. |
| Test Case Workbook | Contains 28 finalized test cases: 10 Login, 10 Forgot Password, and 8 consolidated Social Media cases. |
| Test Data Workbook | Contains broad module-level valid, invalid, boundary, empty, whitespace, format, negative, and security-oriented data in separate tabs. |

# 2. Release Scope

The planned release scope covers the visible and enabled functionality of the OrangeHRM Open Source demo. Actual execution depends on the modules, permissions, integrations, and configuration available during the test window.

## 2.1 In Scope

| Module / Area | Included Functionalities |
| --- | --- |
| Authentication and Login | Valid and invalid login, mandatory fields, masking, keyboard submission, protected-page redirection, logout, session handling, and social links. |
| Forgot Password | Reset-page navigation, username validation, secure responses, duplicate requests, token handling, new-password validation, and post-reset login, where email/reset services are configured. |
| Admin | Users, roles/status, job titles, pay grades, employment status, job categories, work shifts, organization details, locations, qualification master data, localization, and configuration visible to the administrator. |
| PIM and My Info | Employee creation/search, personal and contact details, emergency contacts, dependents, job and salary data, qualifications, attachments, and termination flows. |
| Leave | Leave types, entitlements, apply/assign leave, balances, date validation, approval/rejection, lists, and reports. |
| Time | Customers, projects, activities, timesheets, submission/approval, attendance punches, hour boundaries, and reports. |
| Recruitment | Vacancies, candidates, resume upload, interview scheduling, workflow statuses, offers, and hiring. |
| Performance | KPIs, review creation, evaluation ratings, trackers, date/rating validation, and review workflows. |
| Claim | Events, expense types, claim submission, amount/date validation, attachments, and approval/rejection. |
| Directory and Dashboard | Employee directory search, filters, widgets, quick-launch navigation, and displayed data. |
| Buzz | Posts, comments, likes, deletion/permissions, empty and length validation, special characters, and safe markup handling. |
| Maintenance | Re-authentication, authorized access, employee record operations, and permission checks using disposable records. |
| Cross-cutting Quality | Role-based access, navigation, pagination, date/text validation, responsive behavior, browser compatibility, accessibility checks, session timeout, and safe input handling. |

## 2.2 Out of Scope

OrangeHRM paid or cloud-only modules not enabled in the public Open Source demo.

Production data migration, production deployment, disaster recovery, and live-environment validation.

Full penetration testing, exploit development, denial-of-service testing, or intrusive security scanning.

Formal performance, load, stress, endurance, and capacity certification unless a stable dedicated environment is provided.

Third-party social media platform functionality beyond validating the displayed OrangeHRM link, secure destination, and new-tab behavior.

Email delivery infrastructure when SMTP or reset-mail services are not configured.

Mobile native applications and unsupported browser or operating-system combinations.

Localization languages, payroll, integrations, APIs, or reports that are not enabled or documented for the active demo configuration.

Permanent destructive changes to shared demo data. Purge, delete, terminate, hire, or configuration scenarios use disposable synthetic records only.

Scope control Any newly requested module, browser, integration, or non-functional test type requires impact analysis and approval through change control.

# 3. Test Objectives

Validate that in-scope functions operate according to the documented user stories, acceptance criteria, and observable OrangeHRM behavior.

Detect functional, validation, navigation, data-integrity, usability, accessibility, compatibility, authorization, and basic security-handling defects before release acceptance.

Confirm that valid data is accepted and persisted correctly, while invalid, empty, boundary, malformed, whitespace, special-character, negative, and security-pattern inputs are handled safely.

Verify role-based access and ensure unauthorized users cannot directly access restricted functions.

Confirm end-to-end business flows across employee management, leave, time, recruitment, performance, claims, and supporting modules.

Maintain requirement-to-test traceability and provide objective evidence for release readiness.

Communicate quality status, blockers, residual risks, and a release recommendation to stakeholders.

# 4. Test Strategy

## 4.1 Test Levels and Types

| Test Type | Approach |
| --- | --- |
| Smoke Testing | Validate application availability, login, core navigation, and critical module access for each candidate build or environment reset. |
| Functional Testing | Execute positive and negative scenarios for all in-scope workflows and acceptance criteria. |
| Integration / End-to-End Testing | Validate connected flows such as create employee to search, entitlement to leave request, vacancy to hire, and claim creation to approval. |
| Regression Testing | Re-execute critical and impacted cases after fixes, configuration changes, or demo resets. |
| UI and Usability Testing | Check labels, messages, alignment, navigation, consistency, and user feedback. |
| Compatibility and Responsive Testing | Run critical workflows in supported desktop browsers and inspect responsive behavior at representative desktop, tablet, and mobile viewport sizes. |
| Accessibility Checks | Perform keyboard navigation, focus visibility, accessible-name, form-label, and basic screen-reader checks. |
| Authorization and Basic Security Validation | Test role restrictions, direct URL access, session behavior, safe input handling, secure links, and safe file-upload validation. No intrusive exploitation. |
| Data Validation Testing | Use equivalence classes, boundary values, decision combinations, empty/null-like values, invalid formats, whitespace, special characters, and negative data. |
| Exploratory Testing | Conduct time-boxed exploration around high-risk workflows and areas affected by defects. |

## 4.2 Test Design Techniques

Requirements-based testing and acceptance-criteria coverage

Equivalence partitioning

Boundary-value analysis

Decision-table testing for role, status, and workflow combinations

State-transition testing for recruitment, leave, claim, timesheet, and review statuses

Negative and error-guessing techniques

Risk-based prioritization

Pairwise selection for browser, role, and data combinations where exhaustive coverage is impractical

## 4.3 Execution Method

Run smoke tests before detailed execution.

Execute critical and high-priority tests first, followed by medium and low-priority coverage.

Record actual results, evidence, execution status, environment, and build/date for every test run.

Log reproducible defects with severity, priority, steps, expected and actual results, evidence, and environment details.

Retest resolved defects and run targeted regression around impacted modules.

Update the RTM and daily status metrics throughout execution.

Complete exit-criteria assessment and issue a test summary and release recommendation.

## 4.4 Tools

| Purpose | Proposed Tool / Method |
| --- | --- |
| Test management and traceability | Excel workbooks for RTM, test cases, execution status, and test data; Azure DevOps or Jira may be used if available. |
| Defect management | Approved organizational defect tracker such as Azure DevOps or Jira. |
| Browser testing | Microsoft Edge and Google Chrome; Firefox as an additional compatibility browser if supported. |
| UI inspection | Browser developer tools and responsive device emulation. |
| Accessibility | Keyboard-only testing, browser accessibility tree, and an approved screen reader or accessibility checker. |
| Evidence | Screenshots, screen recordings where permitted, browser console/network details, and exported reports. |
| Automation | Optional Selenium, Playwright, or Katalon for stable smoke/regression flows after manual baseline approval. |

# 5. Test Environment and Test Data

## 5.1 Environment Requirements

| Component | Requirement |
| --- | --- |
| Application | OrangeHRM Open Source demo or a dedicated test deployment with the target configuration. |
| Client Hardware | Standard business laptop/desktop with at least 8 GB RAM and 1366 x 768 or higher display. |
| Operating System | Supported Windows desktop environment; an additional supported OS may be included if required. |
| Browsers | Current organizationally supported versions of Edge and Chrome; Firefox where required. |
| Network | Stable internet access, HTTPS access to OrangeHRM and approved social destinations, and access to configured mail services. |
| Accounts and Roles | Administrator, ESS employee, supervisor/reviewer, and other configured roles using synthetic users. |
| Integrations | SMTP/reset-mail service and file storage if those flows are in scope and available. |
| Utilities | Spreadsheet application, defect tracker, screenshot utility, browser developer tools, and accessibility tools. |
| Test Data Reset | Documented process to recreate synthetic users, employees, vacancies, projects, leave balances, claims, and workflow records after a shared-demo reset. |

## 5.2 Test Data Plan

The prepared test-data workbook contains separate tabs by functional area and includes synthetic positive, negative, boundary, empty/null-like, invalid-format, special-character, whitespace, and basic security-oriented data.

Use only fictitious names, contacts, candidate records, employee records, organizations, IDs, files, and business transactions.

Use Admin / admin123 only where the public demo explicitly provides that account.

Create disposable synthetic accounts for destructive or state-changing scenarios.

Replace configuration-dependent placeholders such as minimum/maximum length with actual environment values before execution.

Generate expired, used, malformed, and valid reset tokens only in a controlled environment.

Keep upload files non-sensitive and scan them according to organizational policy.

Never use real personal, confidential, production, or customer data.

# 6. Resources and Effort Estimate

| Role | Qty. | Primary Responsibilities | Estimated Effort |
| --- | --- | --- | --- |
| QA Lead / Test Manager | 1 | Planning, review, coordination, risk management, metrics, sign-off package | 8 person-days |
| Manual QA Engineer | 2 | Test preparation, execution, evidence, defect logging, retest, regression | 24 person-days total |
| Automation QA Engineer | 1 part-time | Automate stable smoke/regression coverage and maintain scripts | 6 person-days |
| Environment / Application Support | 1 part-time | Access, accounts, configuration, data reset, issue investigation | 3 person-days |
| Business / Product Reviewer | 1 part-time | Scope confirmation, requirement clarification, UAT support, approval | 2 person-days |
| Developer / Defect Owner | As needed | Defect analysis, fixes, unit evidence, deployment support | 8 person-days allowance |

Total planned effort: approximately 51 person-days, including defect-fix support. Effort excludes formal load testing, full security assessment, and major scope changes.

# 7. Test Deliverables

| Deliverable | Owner | Completion Point |
| --- | --- | --- |
| Approved Test Plan | QA Lead | Before test execution |
| User Stories and Acceptance Criteria | Business / QA | Before detailed test design |
| Requirement Traceability Matrix | QA | Before execution; updated through closure |
| Test Cases and Test Data | QA | Before execution; maintained during testing |
| Environment Readiness Checklist | Environment Owner / QA | Before smoke testing |
| Execution Evidence and Daily Status | QA | During execution |
| Defect Reports and Defect Metrics | QA / Development | During execution and retest |
| Regression Results | QA | After fixes and before closure |
| Test Summary Report | QA Lead | At test closure |
| Release Recommendation and Residual Risk Log | QA Lead / Stakeholders | Before release decision |
| Approval Record | Authorized Stakeholders | Before execution and at closure |

# 8. Schedule and Milestones

Schedule assumption The following four-week plan begins Monday, 7 September 2026. Dates should be baselined after team availability and environment readiness are confirmed.

| Phase | Start | Finish | Milestone / Output |
| --- | --- | --- | --- |
| Test-plan review and approval | 7 Sep 2026 | 8 Sep 2026 | Approved scope, strategy, resources, risks, and schedule |
| Environment and account readiness | 7 Sep 2026 | 9 Sep 2026 | Environment checklist passed; roles and synthetic data available |
| Test-case and data finalization | 7 Sep 2026 | 10 Sep 2026 | Cases, AC mapping, RTM, and data baselined |
| Smoke testing | 11 Sep 2026 | 11 Sep 2026 | Build/environment accepted for detailed testing |
| Functional execution Cycle 1 | 14 Sep 2026 | 18 Sep 2026 | All critical/high cases executed; defects logged |
| Defect fixing and continuous retest | 15 Sep 2026 | 25 Sep 2026 | Resolved defects verified; impacted tests rerun |
| Functional execution Cycle 2 and regression | 21 Sep 2026 | 25 Sep 2026 | Remaining tests and regression completed |
| Exploratory, compatibility, and accessibility pass | 24 Sep 2026 | 28 Sep 2026 | Risk-based supplemental results recorded |
| Closure assessment and report drafting | 29 Sep 2026 | 30 Sep 2026 | Exit criteria evaluated; summary prepared |
| Stakeholder review and final sign-off | 1 Oct 2026 | 2 Oct 2026 | Release recommendation and formal approval |

# 9. Entry, Suspension, Resumption, and Exit Criteria

## 9.1 Entry Criteria

Test plan and scope reviewed

Requirements and acceptance criteria available

Test cases, test data, and RTM baselined

Environment accessible and stable

Required accounts and permissions available

Known limitations documented

Smoke-test prerequisites ready

## 9.2 Suspension and Resumption Criteria

Suspend affected testing when the application is unavailable, critical navigation/login is broken, test data cannot be restored, or a blocker prevents meaningful execution.

Resume after the blocking issue is resolved, a replacement environment or workaround is approved, smoke tests pass, and impact is communicated.

## 9.3 Exit Criteria

100% of planned critical and high-priority tests executed

At least 95% of all planned tests executed, excluding formally approved blocked or not-applicable cases

No open Critical defects

No open High defects unless explicitly accepted with documented mitigation and owner

At least 90% overall pass rate, with failures analyzed and dispositioned

All resolved Critical and High defects retested successfully

Required regression completed

RTM updated and no in-scope requirement left without coverage

Test Summary Report and residual-risk log reviewed

Formal release recommendation recorded

# 10. Defect Management

| Severity | Definition | Target Handling |
| --- | --- | --- |
| Critical | Application or critical business flow unavailable; security or data-integrity impact with no workaround | Immediate triage; blocks affected release decision |
| High | Major function fails or produces materially incorrect result; limited workaround | Prioritize for current test cycle and rerun regression |
| Medium | Function partially impaired with a reasonable workaround | Plan fix based on release risk |
| Low | Minor UI, wording, or low-impact issue | Fix as capacity permits or defer with approval |

Bug Priority is assigned separately from severity based on business urgency, release impact, dependency, and stakeholder decision. Every defect should include module, environment, role, reproducible steps, test data, expected result, actual result, evidence, severity, priority, and linked test case.

# 11. Risks and Mitigation Plan

| ID | Risk | Probability / Impact | Mitigation | Contingency / Owner |
| --- | --- | --- | --- | --- |
| R1 | Shared public demo data may be changed or reset by other users. | High / High | Use uniquely prefixed synthetic records; capture evidence; execute stateful flows in short sequences. | Recreate data or move to a dedicated environment / Environment Owner |
| R2 | Forgot-password email or reset-token flow may not be configured. | High / Medium | Confirm SMTP and token access during readiness review. | Mark dependent cases Blocked and execute validation/navigation coverage / QA Lead |
| R3 | Modules or fields may differ by role, version, or configuration. | Medium / High | Perform configuration discovery and map available functions before execution. | Raise scope change and adjust RTM/test cases / QA Lead |
| R4 | Destructive tests may affect shared records. | Medium / High | Use disposable synthetic records and restrict purge/delete scenarios. | Restore or recreate records; defer unsafe scenarios / Application Owner |
| R5 | External social platforms may be unavailable or require sign-in. | Medium / Low | Validate link, HTTPS destination, and new-tab behavior rather than third-party content. | Record external dependency and retest later / QA |
| R6 | Insufficient roles or permissions may block workflow testing. | Medium / High | Create and verify role-specific accounts before execution. | Escalate access request; mark blocked with owner/date / Environment Owner |
| R7 | Browser/version differences may cause inconsistent results. | Medium / Medium | Baseline supported versions and run a risk-based compatibility matrix. | Limit release claim to tested browsers / Product Owner |
| R8 | Unclear configured field limits may weaken boundary coverage. | Medium / Medium | Inspect validation rules and replace placeholders before execution. | Document assumed limits and residual risk / QA |
| R9 | High defect volume may compress regression time. | Medium / High | Prioritize critical flows, daily triage, and continuous retest. | Extend schedule or reduce low-risk scope with formal approval / Test Manager |
| R10 | Security-pattern inputs could be misused outside the authorized environment. | Low / High | Use only benign inputs in approved environments and prohibit intrusive testing. | Stop testing and escalate any unexpected security exposure / Security Contact |
| R11 | Test-data privacy or accidental real-data use. | Low / High | Use synthetic data only; review uploads and evidence before sharing. | Delete exposed data and follow incident process / Test Manager |
| R12 | Automation may be unstable against a changing shared demo. | Medium / Medium | Automate only stable smoke/regression paths with robust locators and waits. | Use manual execution as fallback / Automation QA |

# 12. Reporting, Metrics, and Governance

Daily execution status: planned, executed, passed, failed, blocked, not executed, and not applicable.

Defect status by severity, priority, module, age, and resolution state.

Requirement and acceptance-criteria coverage through the RTM.

Retest and regression progress after fixes.

Environment downtime, blockers, and schedule variance.

Final pass rate, defect leakage risk, unresolved defects, and release recommendation.

## 12.1 Communication Cadence

| Meeting / Report | Frequency | Participants | Purpose |
| --- | --- | --- | --- |
| Daily QA status | Daily during execution | QA team, QA Lead | Progress, blockers, defects, next-day plan |
| Defect triage | Daily or as needed | QA, development, product owner | Severity, priority, ownership, fix target |
| Milestone review | End of each cycle | QA Lead and stakeholders | Coverage, quality trend, schedule, risk |
| Closure review | End of testing | All approvers | Exit criteria, residual risk, go/no-go recommendation |

# 13. Review and Approval Process

QA Lead circulates the draft Test Plan and linked artifacts to stakeholders.

Business, technical, environment, and QA reviewers verify scope, objectives, assumptions, estimates, schedule, risks, and exit criteria.

Review comments are resolved and material changes are recorded in document history.

Approvers record name, role, decision, date, and comments in the approval table.

Testing begins only after approval or a documented exception by the authorized stakeholder.

Any major post-approval change follows change control and triggers impact analysis for scope, schedule, resources, test cases, data, and risks.

## 13.1 Approval Record

| Approver Role | Name | Decision | Date | Comments / Signature |
| --- | --- | --- | --- | --- |
| QA Lead / Test Manager |  | Pending |  |  |
| Business / Product Owner |  | Pending |  |  |
| Technical / Application Owner |  | Pending |  |  |
| Environment Owner |  | Pending |  |  |

# 14. Change History

| Version | Date | Author | Change Summary |
| --- | --- | --- | --- |
| 1.0 | 2 Sep 2026 | Test Planning Team | Initial test plan based on finalized OrangeHRM user stories, RTM, test cases, and test data. |